## Sheet1
Hours Spent on Blessed Sacrament Parish (BSP) and Roncalli Newman Website Redesigns
Andrew Krause, November 2024 - January 2025
Date | Hours Spent | Description of Work
2024-11-07 | 1 | Created base template for new Blessed Sacrament Parish (BSP) website on squarespace.
2024-11-09 | 2 | Created a UI design draft and began planning work for both websites. Also began working on the new BSP website homepage.
2024-11-10 | 1 | Worked on the homepage of the new BSP website and updated the header.
2024-11-11 | 3 | Worked on the homepage of the new BSP website.
2024-11-12 | 3 | Worked on the homepage of the new BSP website, updated footer of website, and created a separate Mass Times page.
2024-11-13 | 2 | Worked on bulletin page of the new BSP website.
2024-11-14 | 0 | No work done today.
2024-11-15 | 2 | Worked on the becoming Catholic and sacraments pages of the new BSP website.
2024-11-17 | 6 | Worked on events page of the new BSP website.
2024-11-18 | 4 | Continued work on the sacraments page and updated the Mass times page of the new BSP website.
2024-11-19 | 4 | Worked on the staff and contact pages of the new BSP website.
2024-11-20 | 3 | Applied some of Adele's feedback to the new BSP website design.
2024-11-26 | 6 | Added more pages for ministries.
2024-11-27 | 4 | Added more pages for ministries.
2024-11-29 | 3 | Updated page design plans and reviewed work.
2024-12-03 | 2 | Added header images to pages.
2024-12-04 | 6 | Updated Ministries page.
2024-12-05 | 4 | Updated Ministries pages.
2024-12-10 | 5 | Added Women's Club and Catholic Resources pages.
2024-12-11 | 4 | Applied new fonts to the website.
2024-12-12 | 4 | Created information architecture diagram and GitHub repository.
Total Hours Worked | 69 | This work took place from November 2024 to January 2025.
Total Money Earned (if charging $35 per hour) | 2415 | This value is based on a calculation that assumes you are making $35 per hour.